## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Rusheek G | 2024-12-21 | Sentiment Analysis misclassifies neutral reviews | Sprint 1 | Rusheek G | Model Accuracy | Fine-tuned model with additional training data | 2025-01-15 | Closed | Accuracy improved by 10%
2 | Rusheek G | 2024-12-21 | Google /Email Sheets API fails to fetch data intermittently | Sprint 2 | Rusheek G | API Integration | Implemented retry mechanism and logging | 2025-01-18 | Closed | Issue resolved after fix
3 | Rusheek G | 2025-01-17 | Personalized recommendations not updating | Sprint 3 | Rusheek G | Logic Error | Fixed cache invalidation issue | 21/1/1025 | Closed | System now updates correctly
4 | Rusheek G | 2025-01-27 | Emails not sending for some users | Sprint 4 | Rusheek G | Email Service Bug | Updated email service and retry logic | 2025-01-29 | Closed | Delivery rate improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others